## Application Planner
Grad School Application Planner | [7 empty] | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) | [7 empty] | Change the date to match the program deadline | [18 empty] | Post Application
Select a week to highlight at right. A legend describing the charting follows. |  |  |  |  | Week Highlight: | 5 | [31 empty] | GRE | [19 empty] | END
WEEKS
CATEGORY | ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | time axis 2020-12-23 to 2022-05-25
 | time axis 2020-12-23 to 2022-05-25
RESEARCH SCHOOLS | Research Schools | 19 | 18 | 19 | 1 | 0%
| Request Info from Schools | 27 | 10 | 27 | 1 | 0%
| Contact Prospective Professors | 27 | 10 | 27 | 1 | 0%
GRE AND OTHER EXAMS | (IS) Study for TOEFL or IELTS | 19 | 4 | 19 | 1 | 0%
| (IS) Take TOEFL or IELTS | 23 | 1 | 23 | 1 | 0%
| Study for GRE | 23 | 10 | 23 | 1 | 0%
| Take GRE | 32 | 1 | 32 | 1 | 0%
| Retake GRE if Needed | 32 | 14 | 45 | 1 | 0%
| GRE Subject Test | 45 | 4 | 45 | 1 | 0%
STATEMENT OF PURPOSE | Draft Statement of Purpose | 32 | 4 | 32 | 1 | 0%
| Finalize SoP | 45 | 5 | 45 | 1 | 0%
APPLICATION PACKET | Create Application Account | 19 | 34 | 19 | 1 | 0%
| Fill out personal information | 19 | 34 | 19 | 1 | 0%
| Send Transcripts | 40 | 5 | 40 | 1 | 0%
| Ask for Recommendations | 35 | 8 | 35 | 3 | 0%
| Submit Resume / CV | 19 | 34 | 19 | 1 | 0%
| Professional Development Docs | 19 | 34 | 19 | 1 | 0%
| Submit Test Scores | 19 | 34 | 19 | 1 | 0%
| Citizenship Verification | 19 | 34 | 19 | 1 | 0%
| Personal Statement | 32 | 18 | 32 | 1 | 0%
| Submit Application | 45 | 8 | 45 | 1 | 0%
FUNDING | Research Funding Opportunities | 18 | 35 | 0 | 0 | 0%
| NSF GRFP | 32 | 13 | 0 | 0 | 0%
| Other Funding | 0 | 0 | 0 | 0 | 0%
| Other Funding | 0 | 0 | 0 | 0 | 0%
RESPONSE | Admission Decision | 60 | 11 | 0 | 0 | 0%
| Interviews | 60 | 11 | 0 | 0 | 0%
| Selection | 64 | 7 | 0 | 0 | 0%
| Other Activity 1 | 0 | 0 | 0 | 0 | 0%
| Other Activity 2 | 0 | 0 | 0 | 0 | 0%
| Other Activity 3 | 0 | 0 | 0 | 0 | 0%
| Other Activity 4 | 0 | 0 | 0 | 0 | 0%
| Other Activity 5 | 0 | 0 | 0 | 0 | 0%
| Other Activity 6 | 0 | 0 | 0 | 0 | 0%
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Include following up / responding to offers, etc.

## Funding Sources
Organization | Program | Website
National Science Foundation | GRFP | https://www.nsfgrfp.org/
Association of Environmental Engineering and Science Professors | General | https://www.aeesp.org/jobs
The National GEM Consortion | GEM | https://www.gemfellowship.org/
Environmental Protection Agency | STAR | https://www.epa.gov/research-grants
American Society of Civil Engineers | ASCE | https://www.asce.org/asce_fellowships/
In PhD
RWJF | HPRS | https://healthpolicyresearch-scholars.org/
University Centers for Exemplary Mentoring (UCEM) | Sloan Fellowship-GT | https://ceed.gatech.edu/sloan-foundation-fellowship
| ARCS | https://atlanta.arcsfoundation.org/scholar-news

## Directory
Institution | Graduate Admission | Financial Aid | Bursar | Institute Catalog | Institute Graduate Degree Programs | International Student Scholars Services
Ga Tech | https://www.grad.gatech.edu/contact-us | https://finaid.gatech.edu/contacting-our-office | https://bursar.gatech.edu/node/1 | https://catalog.gatech.edu/ | https://www.grad.gatech.edu/degree-programs | https://oie.gatech.edu/isss/home